## Slide 1: Abbott Vascular Digital and Analytics Application

## Slide 2: HCL’s understanding of the Vascular Digital and Analytics Application
  As part of Digital health initiative to build a Scalable Digital infrastructure and host the vascular data from the providers to enable development and roll out of digital and analytics applications.
  Data Sources
  From Cathlabs using the IoT based ingestion that will contain the following:
  Case Information/Repository (Patient details, demographics, medical history, co-morbodities, Images etc.)
  Information from the Powerapp applications that contain the clinical procedures followed for the patient. This is obtained using the Data verse integration available
  Additional data that needs to be acquired and used for analytics include
  Data from the SFDC and marketing tool used by the sales/marketing teams
  Mobile application that is being in trial now to obtain the post procedure data to track patient’s recovery
  Provide information on :
  Architecture and Solution visualization for the platform (similar to EP cloud and Merlin.Net programs)
  Data Aggregator and Data Catalog design thoughts for Data Scientists and Domain experts to build solutions.
  Handle around 2500 patients with larger dataset from the marketing tools.
  Resources required to build the solution, data engineers etc., to build the platform
  Proposal encompassing the solution, resources and the business model for engagement

## Slide 3: Solution Overview
Case Information Repository
Dataverse (PowerApps)
SFDC and marketing tool
Mobile App
Hospital / Clinical / Patient Data Providers
Data Aggregator/ Workflow/Rule Engine
Vascular Digital and Analytics Platform
Authentication &
Authorization
Analytics Service
Vascular
Applications
API Gateway
IOT Hub
DB
Multitenant
Surgeons
Data Scientists
Handle < 2500 patients, ~100K Prospects
Data Catalog
Module
Provider Applications
Other Abbott Applications
Audit / Logging
Module
Platform Users

## Slide 4: Component Flow

## Slide 5: Engagement Model – Option 1 (Abbott managed T&M)
Program Manager
Abbott
HCL
HCL Onsite
HCL Offshore
Abbott SMEs
HCL Onsite engineers
HCL Offshore team
HCL Project manager
Program management will be owned by Abbott
Work assignation designed and decided by Abbott program manager
HCL will deploy the skilled resources based on the program need
HCL team members will participate in Abbott SCRUM process and deliver as per the project plan formulated by Abbott PM

## Slide 6: Option #1 Commercials – Rate card
Sl.No | Role | Skill | No.Of . Persons | Exp. | Rate Card
1 | Azure Solution Architect | Azure IAAS solution development | 1 | 15+ Years | $40.00
2 | Technical Co-ordinator (Onsite) | Bridge the Offshore and Onsite teams and getting requirements clarity from Product owners. Technical Skills : C# and .Net | 1 | 15 + Years | $120.00
3 | Technical Lead | Core Azure Services, C#, .Net (Backend) | 1 | 10+ Years | $29.00
4 | Technical Lead | IOT Hub, Application API integration, C# and .Net (Backend) | 1 | 10+ Years | $29.00
5 | Software Developer | C#, .Net | 3 | 6+ Years | $27.00
6 | UI Lead | Angular/React experience , CSS, HTML | 1 | 10+ Years | $29.00
7 | UX Lead | User Experience | 1 | 10+ Years | $29.00
8 | UI Developers | Angular/React experience , CSS, HTML | 2 | 6+ Years | $27.00
9 | Test Lead | Testing | 1 | 12 + Years | $29.00
10 | Test Team | Manual Testers | 3 | 6+ Years | $24.00
11 | Test Team | Automation | 3 | 6+ Years | $24.00
12 | DevOps Lead | Azure DevOps | 1 | 10+ Years | $29.00
13 | DevOps Engineer | Azure DevOps | 1 | 6+ Years | $27.00
14 | Data Engineer | Big Data Experience | 1 | 6+ Years | $29.00
15 | Cloud Infra Architect | Azure cloud Infra Architect | 1 | 10+ Years | $40.00
16 | Engineering/Project Manager |  | 1 | 12+ Years | $31.00
17 | Business Analyst/SCRUM Master |  | 1 | 10+ Years | $29.00
18 | Technical Writer |  | 1 | 10+ Years | $27.00
19 | Data Scientist * | AI / ML | 1 | 10+ Years | $140.00
 |  |  | Infrastruture cost |  | 

## Slide 7: Engagement Model – Option 2 (HCL managed T&M)
Program Manager
Abbott
HCL
HCL Onsite
HCL Offshore
Abbott SME team
HCL Onsite engineers
HCL Offshore team
HCL Project manager
HCL – team
Program management will be owned by HCL
Work assignation designed and decided by HCL program manager
HCL will deploy all the skilled resources required for this program
HCL will drive SCRUM meetings along with Abbott SMEs and deliver as per the project plan

## Slide 8: Key Architectural and Technical Considerations
Case Information Repository
Dataverse (PowerApps)
SFDC and marketing tool
Mobile App
Hospital / Clinical / Patient Data Providers
Data Aggregator/ Workflow/Rule Engine
Vascular Digital and Analytics Platform
Authentication &
Authorization
Analytics Service
Vascular
Applications
API Gateway
IOT Hub
DB
Multitenant
Surgeons
Data Scientists
Handle < 2500 patients, ~100K Prospects
Data Catalog
Module
Provider Applications
Other Abbott Applications
Audit / Logging
Module
Platform Users
Data Perimeter Security Policies
Horizontal Scaling as per Surge
Ease of Operations
Batch Processing with Incremental data fetch
Realtime Processing
Async / Non-Blocking Processing
Secure – Third party integration with A&A
2. Provide the separate topic to push / Notify
for the new data
Rule based data aggregation.
Workflow/Orchestration based data filtering – transformation – fulfilment
Schema driven Data Validation
Backpressure handling for the incoming messages
Scalable - Horizontally w.r.t Storage and Processing.
Multi-tenant – Logical separation of data across providers.
To handle mutli data models(SQL, NoSQL, Timeseries etc.)
Multi – Dimensional data storage
Meta-Data driven data discovery
Data API and visualization interface
Enforcement of Data Access Policy
Data Security During transit and
Storage

## Slide 9: CARE Vs Azure native for Product Development
Sl. No | CARE | Azure Native
Sl. No | CARE | Azure Native
1 | Have predefined Entity management, User management, Device Management features which can be readily usable | Need to write customized .NET code to implement Entity management, User management, Device management features
2 | Entity relationship among various entities were already defined and owned by CARE team | We must define the ER relationship for each entity
3 | CARE features are available as service api’s and can be dockerized and used in any cloud environment | Azure native code relies of Azure native libraries and works only in Azure environment and can’t be ported to any other cloud environment.
4 | Wait time to use CARE service is nil | We have wait for the service to be built and available for project team to use
5 | CARE relies on third party services like Microsoft communication service or SendGrid for MFA token deliver to end user mobile/email | Azure has its own services that can be used to deliver MFA token to end user mobile/email
6 | CARE can be customized to any feasible extent based on user requirements | Azure native relies on native libraries to implement so we have limited scope for customization

## Slide 10: Functional Assumptions and Dependencies
Assumptions | Dependencies
Dataverse will be used for obtaining procedure details performed on the patient. It is understood that this data is originating in the provider as PowerApps data and is made available via Dataverse | Dataverse schema definition and interface details need to provided.
Patient EMR related information will be available Case Information Repository. This information will be exposed through IOT Hub | IOT Hub integration details and schema details will be provided.
Post procedure data to track patient’s recovery will be provided from Mobile App Data source through API Gateway | API Gateway details and schema definition will be made available
SFDC and marketing tool data will be used by the sales/marketing teams | SFDC and marketing tool integration details and data schema details need to be shared.
It is understood that in future the data may come from Other Abbott applications and system should be provisioned to handle the data. | Needs to work with Abbott for future other Abbott applications data collection.
Data Aggregation will be driven by Workflow and Rule Engine definitions. | Workflow and Rule Engine definitions need to be agreed and finalized.

## Slide 11: Functional Assumptions and Dependencies
Assumptions | Dependencies
It is understood that the aggregated data will be stored Multi tenant data base. | The DB schema and definition should be finalized.
Data catalog will be used to provide the details about the data reside in multi tenant data base. This information will be utilized to south bound applications like Vascular and Analytics Applications | Catalog definition and tool needs to be finalized.
It is assumed to build one Vascular application and one Analytics (AI) application from the aggregated data stored in the Multi tenant database. | Work with Abbott and finalize the sample vascular application and Analytics applcation.

## Slide 12: Program Timeline
MVP #1 – Aug’21
Base platform setup
MVP #2 – Oct’21
Data aggregation
MVP#3 – Jan’22
Vascular apps development
Catalog initial view
Data sources connectivity and ingestion
Catalog and Data API
Rule Engine
Analytical services development
Demo - One Vascular application & one AI Model
Demo - Catalog final view
Demo - Data ingestions and Catalog Initial View
Data Structure Definition for Solution

## Slide 13: Detailed Program Timeline
Data structure for the application
Base Platform setup initiation
Team ramp up
Rule Engines definitions
Mobile app data acquisition plan
MVP 2
IOT Hub Setup in AKS
MVP 1
Requirements
Definition
CARE Setup in AKS
Integrations
Review
Data verse design understanding and Review
Data verse configuration
Jun
Jul
Aug
Sep
IOT Hub Integration
Catalog Design
Use case identification and planning
IOT Hub Design understanding and Review
MVP1 Milestone Demo
8/27/2021
Abbott
HCL
…….Cont.
……. Cont.….
Onsite -2
Offshore -16
Onsite -2
Offshore -16
Onsite -2
Offshore -5
Catalog requirements
Catalogue Definition
SMEs -3
SMEs -3
SMEs -3
Abbott
HCL
Legend

## Slide 14: Detailed Program Timeline – contd…
Rule Engine Design
Team ramp up
Rule engine
Tool finalization
Data Aggregator Design
Data Aggregator
Implementation
MVP2
Catalog Final View implementation
Catalog finalization
One Analytics Application Requirements
Sep
Oct
Nov
Design Analytics Application
Rule Engine Implementation
MVP2 Milestone Demo
15/10/2021
Abbott
HCL
Onsite -2
Offshore -22
Onsite -2
Offshore -18
…….Cont.
MVP3
Onsite -2
Offshore -19
SMEs -3
SMEs -3
SMEs -3
Data Aggregator Design Review
SFDC and marketing Tool Design understanding and review
SFDC toll data integration design
…….Cont.
Abbott
HCL
Legend
One Analytics Application Requirements

## Slide 15: Detailed Program Timeline – cont.…
Analytics – One AI Model Requirements
Vascular Application UI Wireframe
Model Training Complete
MVP3
Model Testing / Development Complete
Dec
Jan
Vascular Application development Complete
Abbott
HCL
Onsite -2
Offshore -19
Onsite -2
Offshore -19
SMEs -3
Data for the AI Model
AI Model Design
MVP3 Milestone Demo
01/28/2022
Production
Abbott
HCL
Legend
AI Model requirements

## Slide 16: MVP Features and Dependencies
Phase | Feature/functionality | Dependency | Complexity level
MVP1 | Dataverse Integration | Data Structure definition and types | High
MVP1 | IOT Hub Integration | Data Structure definition | High
MVP1 | Mobile App Data Collection | Availability of standard interface to acquire data | Low
MVP2 | Rule engine implementation | Rules definitions | High
MVP2 | Catalog Implementation | Catalog definition | Medium
MVP2 | Data aggregator Implementation | Rules definitions | High
MVP3 | Vascular apps Implementation | Details around Vascular Apps and Review | Medium - High
MVP3 | Analytics Sample Application | Identify Sample AI Model/application | Medium - High

## Slide 17: Commercials – Indicative Costing
Note: This is only indicative cost structure based on the requirement assumptions. Accurate estimate will be derived once the requirements are thoroughly hashed out with Abbott SMEs as part of MVP1 phase.
Sl.No | Role | Onsite/Offshore | RateCard | Jun-21 | Jul-21 | Aug-21 | Sep-21 | Oct-21 | Nov-21 | Dec-21 | Jan-22 | Total | Price
1 | Solution Architect | Onsite | $120.00 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 8 | $153,600.00
2 | Technical Co-ordinator (Onsite) | Onsite | $120.00 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 8 | $153,600.00
3 | Business Analyst/SCRUM Master | Offshore | $29.00 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 8 | $37,120.00
4 | Dotnet SME | Offshore | $29.00 | 1 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 11 | $51,040.00
5 | CARE SME | Offshore | $29.00 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 4 | $18,560.00
6 | Devops | Offshore | $29.00 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 15 | $69,600.00
7 | .Net Senior Dev | Offshore | $29.00 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 14 | $64,960.00
8 | .Net Junior Dev | Offshore | $27.00 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 14 | $60,480.00
9 | Angular Dev | Offshore | $29.00 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 14 | $64,960.00
10 | Test Lead | Offshore | $27.00 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 7 | $30,240.00
11 | Manual Testers | Offshore | $24.00 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 10 | $38,400.00
12 | Tes Automation Engineers | Offshore | $24.00 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 10 | $38,400.00
13 | Data Sciense Analyst | Offshore | $29.00 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 5 | $23,200.00
14 | DB Engineer | Offshore | $29.00 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 5 | $23,200.00
15 | Cloud Infra Architect | Offshore | $29.00 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 3 | $13,920.00
16 | Enginering Manager/Project Manager | Offshore | $31.00 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 7 | $34,720.00
21 | Technical Writer | Offshore | $27.00 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 8 | $34,560.00
 |  |  |  | 7 | 18 | 18 | 24 | 21 | 21 | 21 | 21 |  | $910,560.00

## Slide 19: Industry View – Monetizing Lab Data
Digital Enablement
Data Management Solution –Segregating Data Processing from Instrument Management
5M per upgrade saving
Dynamic Assay
Decouple Calculations and Assay development from device – Deliver Assays OTA
Maximize Return on R&D
AI Enablement
Remote Information Systems Platform for Bio-information Research and AI
Integrate Internal-External Data Ontologies
Clinical Decision Support
Laboratory Test data based clinical intelligence
> 700 Million USD in Revenue
SERVICE INTELLIGENCE
PROCESS INTELLIGENCE
CLINICAL INTERVENTION
DATA CORE
Remote Servicing
EFFICIENT WORKFLOW
Track the Sample and Data over the entire Sequencing flow to increase efficiency of lab processes
Increase Operational Efficiency
1
2
4
5
3
Workflow Management

## Slide 20: Data As A Service based Rapid Collaboration Platform
Build and Operate a cloud based Data Ontology platform for collaborative bio-informatics research
Short Term HUB
HETEROGENOUS CONNECTIVITY
Integration
Hub
Data Visibility & Access
Data Enrichment Hub
Data Lake [ePHI & non-ePHI]
VISUALIZATION
Analytics
> 1TB GENOME DATA RIVER
Data Lineage – Guaranteed Data Management Governance Integrity & Traceability
AI/ML/DL PIPELINE
Micro Services
APIS
Guaranteed Data Veracity
Cloud Digital Platform
Catalog
Multi Tenancy
Security
Data Catalog
Data Privacy
High Volume
Data Leniency
Data Archiving
Secure Compute Platform
Bio-informatics Pipelines
HPC
Collaborators Device & Software Systems